## Estimates
Epic | Story | Points | Estimated Hours | Completed | Completed Points | Completed Hours
Project Setup | Information Architecture Diagram | 1 | 4 | TRUE | 1 | 4
Project Setup | Define Roles | 1 | 4 | TRUE | 1 | 4
Project Setup | Git Repository | 1 | 4 | TRUE | 1 | 4
Project Setup | Visual Studio Solution | 1 | 4 | TRUE | 1 | 4
Project Setup | AppVeyor Build Pipeline | 1 | 4 | TRUE | 1 | 4
Project Setup | Static Code Quality Analysis | 1 | 4 | TRUE | 1 | 4
Project Setup | Project Plan | 2 | 8 | TRUE | 2 | 8
Project Setup | Implementation Plan | 2 | 8 | TRUE | 2 | 8
Project Setup | Application Infrastructure Diagram | 1 | 4 | TRUE | 1 | 4
Project Setup | Application Architecture Diagram | 1 | 4 | TRUE | 1 | 4
Project Setup | Entity Relationship Diagram | 2 | 8 | TRUE | 2 | 8
Project Setup | Admin Blazor Module | 1 | 4 | TRUE | 1 | 4
Project Setup | Entity Framework | 2 | 8 | TRUE | 2 | 8
Project Setup | Estimates | 1 | 4 | TRUE | 1 | 4
Project Setup | Entity Framework Models | 2 | 8 | TRUE | 2 | 8
Project Setup | Serilog Console, File Logging | 2 | 8 | TRUE | 2 | 8
Project Setup | Code Quality Check Razor Pages | 1 | 4 | TRUE | 1 | 4
Project Setup | Code Quality Check Async Methods | 1 | 4 | TRUE | 1 | 4
Project Setup | Setup Deployment | 3 | 16 | TRUE | 3 | 16
Home Page | Home Page Header | 3 | 16 | TRUE | 3 | 16
Home Page | Image Rotator | 2 | 8 | TRUE | 2 | 8
Home Page | Home Page Middle | 2 | 8 | TRUE | 2 | 8
Home Page | Home Page Footer | 2 | 8 | TRUE | 2 | 8
Basic Administration | Login | 3 | 16 | TRUE | 3 | 16
Basic Administration | Logout | 2 | 8 | TRUE | 2 | 8
Basic Administration | Administration Dashboard | 3 | 16 | TRUE | 3 | 16
Basic Administration | Edit Configuration | 5 | 32 | TRUE | 5 | 32
Basic Administration | Edit Home Page | 5 | 32 | TRUE | 5 | 32
Basic Administration | Edit Header | 5 | 32 | TRUE | 5 | 32
Basic Administration | Edit Footer | 5 | 32 | TRUE | 5 | 32
Manage Images and Videos | List Images and Videos | 5 | 32 | TRUE | 5 | 32
Manage Images and Videos | Upload Image | 3 | 16 | TRUE | 3 | 16
Manage Images and Videos | View Image | 2 | 8 | TRUE | 2 | 8
Manage Images and Videos | Delete Image | 2 | 8 | TRUE | 2 | 8
Manage Images and Videos | Rename Image | 2 | 8 | TRUE | 2 | 8
Manage Images and Videos | New Folder | 1 | 4 | TRUE | 1 | 4
Manage Web Pages | List Pages | 3 | 16 | TRUE | 3 | 16
Manage Web Pages | Add Page | 5 | 32 | TRUE | 5 | 32
Manage Web Pages | Edit Page | 2 | 8 | TRUE | 2 | 8
Manage Web Pages | Delete Page | 2 | 8 | TRUE | 2 | 8
Manage Web Pages | Rename Page | 2 | 8 | TRUE | 2 | 8
National Pages | Design National Home Page | 5 | 32 | TRUE | 5 | 32
National Pages | National Home Page | 5 | 32 | TRUE | 5 | 32
National Pages | National About Us Page | 2 | 8 | TRUE | 2 | 8
National Pages | National History of Bed Brigade Page | 2 | 8 |  | 0 | 0
Locations | Location List | 3 | 16 | TRUE | 3 | 16
Locations | Bed Brigade Near Me | 5 | 32 | TRUE | 5 | 32
Locations | Grove City Location Home Page | 3 | 16 | TRUE | 3 | 16
Locations | Grove City Location About Us Page | 2 | 8 | TRUE | 2 | 8
Locations | Grove City History Page | 2 | 8 | TRUE | 2 | 8
Locations | Grove City Partners | 2 | 8 | TRUE | 2 | 8
Locations | Grove City Assembly Instructions | 2 | 8 | TRUE | 2 | 8
Locations | Polaris Location Home Page | 5 | 32 |  | 0 | 0
Locations | Polaris About Us Page | 2 | 8 |  | 0 | 0
Locations | Polaris Assembly Instructions | 2 | 8 |  | 0 | 0
Manage Locations | Manage Locations Page | 5 | 32 | TRUE | 5 | 32
Manage Locations | Edit Location | 3 | 16 | TRUE | 3 | 16
Manage Locations | Add Location | 5 | 32 | TRUE | 5 | 32
Manage Locations | Deactivate/Activate Location | 5 | 32 |  | 0 | 0
Location Request Bed | Request Bed Page | 5 | 32 | TRUE | 5 | 32
Location Request Bed | Manage Bed Requests | 5 | 32 | TRUE | 5 | 32
Location Request Bed | Manage Delivery Checklist | 5 | 32 | TRUE | 5 | 32
Location Volunteer | Volunteer Page | 5 | 32 | TRUE | 5 | 32
Location Volunteer | Manage Volunteers | 5 | 32 | TRUE | 5 | 32
Location Volunteer | Bulk Email Volunteers | 3 | 16 | TRUE | 3 | 16
Location Volunteer | Manage Build and Delivery Schedule | 5 | 32 | TRUE | 5 | 32
Location Contact Us | Contact Us Page | 3 | 16 | TRUE | 3 | 16
Location Contact Us | Manage Contacts | 5 | 32 | TRUE | 5 | 32
Location Donations | Grove City Donate | 3 | 16 | TRUE | 3 | 16
Location Donations | Polaris Donate | 3 | 16 |  | 0 | 0
Location Donations | Manage Donations | 5 | 32 | TRUE | 5 | 32
Location Donations | Email Tax Forms | 5 | 32 | TRUE | 5 | 32
Manage Users | User List | 3 | 16 | TRUE | 3 | 16
Manage Users | Add User | 3 | 16 | TRUE | 3 | 16
Manage Users | Edit User | 3 | 16 | TRUE | 3 | 16
Manage Users | Delete User | 3 | 16 | TRUE | 3 | 16
Stories | Grove City Sample Story | 2 | 8 |  | 0 | 0
Stories | Polaris Sample Story | 2 | 8 |  | 0 | 0
Stories | List of Stories | 3 | 16 |  | 0 | 0
Stories | Story Detail | 3 | 16 |  | 0 | 0
Stories | Manage Stories | 3 | 16 |  | 0 | 0
Stories | Add Story | 3 | 16 |  | 0 | 0
Stories | Edit Story | 1 | 4 |  | 0 | 0
Stories | Delete Story | 1 | 4 |  | 0 | 0
News | National News Sample Story | 3 | 16 |  | 0 | 0
News | List of News | 3 | 16 |  | 0 | 0
News | News Detail | 3 | 16 |  | 0 | 0
News | Manage News | 3 | 16 |  | 0 | 0
News | Add News | 3 | 16 |  | 0 | 0
News | Edit News | 1 | 4 |  | 0 | 0
News | Delete News | 1 | 4 |  | 0 | 0
Tech Debt | Upgrade to Blazor 8 | 5 | 32 | TRUE | 5 | 32
Tech Debt | Refactor Common.cs | 1 | 4 | TRUE | 1 | 4
Tech Debt | Refactor into Files | 1 | 4 | TRUE | 1 | 4
Tech Debt | Move Entities | 1 | 4 | TRUE | 1 | 4
Tech Debt | Move Syncfusion Licensing | 1 | 4 | TRUE | 1 | 4
Tech Debt | Regression Testing | 3 | 16 | TRUE | 3 | 16
Tech Debt | Change from Azure Email to SmarterASP.NET Email | 1 | 4 | TRUE | 1 | 4
Tech Debt | Update Diagrams | 1 | 4 | TRUE | 1 | 4
Tech Debt | GitHub Actions for Pull Requests | 1 | 4 | TRUE | 1 | 4
Tech Debt | Deploy to SmarterASP.NET Development | 1 | 4 | TRUE | 1 | 4
Tech Debt | Use location query parm Bed Request | 1 | 4 | TRUE | 1 | 4
Tech Debt | Use Location Query Parm Contact | 1 | 4 | TRUE | 1 | 4
Tech Debt | Use Location Query Parm Volunteer | 1 | 4 | TRUE | 1 | 4
Tech Debt | Design Shared Bed Requests | 1 | 4 | TRUE | 1 | 4
Tech Debt | Admin Dashboard Content | 1 | 4 | TRUE | 1 | 4
Tech Debt | Unique Volunteer Email Add Dialog | 1 | 4 | TRUE | 1 | 4
Tech Debt | Update NuGet Packages and Change NUnit Assertions | 2 | 8 | TRUE | 2 | 8
Tech Debt | Cache get files | 1 | 4 | TRUE | 1 | 4
Tech Debt | Remove Unused Components and Pages | 1 | 4 |  | 0 | 0
Tech Debt | Add three image rotators to Bed Brigade Near Me | 1 | 4 |  | 0 | 0
Tech Debt | Location Latitude & Longitude | 1 | 4 |  | 0 | 0
Tech Debt | FM Dependent Functionality | 5 | 32 |  | 0 | 0
Tech Debt | Verify security for all pages | 3 | 16 |  | 0 | 0
Tech Debt | Global Error Handler | 3 | 16 | TRUE | 3 | 16
Tech Debt | Refresh Header and Footer | 1 | 4 | TRUE | 1 | 4
Tech Debt | Add Page Titles | 1 | 4 |  | 0 | 0
Tech Debt | Custom Icons in Grid Toolbar | 1 | 4 |  | 0 | 0
Tech Debt | AppOffline for Development | 2 | 8 | TRUE | 2 | 8
Tech Debt | Syncfusion Spinner | 2 | 8 | TRUE | 2 | 8
Tech Debt | Re-add compilerconfig.json | 1 | 4 | TRUE | 1 | 4
Tech Debt | Rework Seeding | 2 | 8 | TRUE | 2 | 8
Tech Debt | Upgrade to Blazor 9 | 2 | 8 |  | 0 | 0
Tech Debt | Blazor 9 Change Render Mode | 2 | 8 |  | 0 | 0
Tech Debt | Add Notification Code to Sorry Page | 1 | 4 | TRUE | 1 | 4
Manage Locations | Metro Areas | 1 | 4 | TRUE | 1 | 4
Locations | Polaris Donations Page | 3 | 16 |  | 0 | 0
New Stories | Send confirmation email for Bed Request | 1 | 4 |  | 0 | 0
Tech Debt | Make seeding environment specific | 1 | 4 | TRUE | 1 | 4
Tech Debt | Import Bed Requests | 3 | 16 |  | 0 | 0
Tech Debt | Add Database Indexes | 1 | 4 |  | 0 | 0
Tech Debt | Verify Mobile for all pages | 1 | 4 | TRUE | 1 | 4
Tech Debt | Refactor Grid Persistence | 2 | 8 | TRUE | 2 | 8
Tech Debt | Add try catch and alert | 3 | 16 |  | 0 | 0
National Pages | National History of Bed Brigade Page | 1 | 4 |  | 0 | 0
National Pages | National Donations Page | 1 | 4 |  | 0 | 0
Location Request Bed | Download Delivery Sheet | 5 | 32 | TRUE | 5 | 32
Location Volunteer | Manage Sign Ups | 5 | 32 | TRUE | 5 | 32
Tech Debt | Seed Only Grove City and Rock City | 1 | 4 | TRUE | 1 | 4
Tech Debt | Bed Request Added to List and Team # | 1 | 4 | TRUE | 1 | 4
Tech Debt | Location Timezone | 3 | 16 |  | 0 | 0
Tech Debt | Redo Manage Bed Request Form | 1 | 4 |  | 0 | 0
Tech Debt | Delivery Sheet Sort By Team Then By Distance | 1 | 4 | TRUE | 1 | 4
Tech Debt | Add Delivery Checklist to the Delivery Sheet | 1 | 4 | TRUE | 1 | 4
Tech Debt | Use Animate.css and Wow.js | 1 | 4 | TRUE | 1 | 4
Tech Debt | Migration Deployment Setup Database and Preload | 1 | 4 | TRUE | 1 | 4
Tech Debt | Improve Performance | 3 | 16 | TRUE | 3 | 16
Tech Debt | Edit EmailTaxForm | 1 | 4 | TRUE | 1 | 4
Tech Debt | Create Custom Authentication | 1 | 4 | TRUE | 1 | 4
Tech Debt | Create Server Information Page | 1 | 4 | TRUE | 1 | 4
Tech Debt | Refresh Header and Footer | 1 | 4 | TRUE | 1 | 4
Tech Debt | Refactor Grid Persistence | 2 | 8 | TRUE | 2 | 8
Tech Debt | Seed Only Grove City and Rock City | 1 | 4 | TRUE | 1 | 4
Tech Debt | Download Delivery Sheet | 5 | 32 | TRUE | 5 | 32
Tech Debt | Mobile Bed Brigade Near Me | 1 | 4 |  | 0 | 0
Tech Debt | Mobile After Submit Bed Request | 1 | 4 |  | 0 | 0
Tech Debt | Mobile after Contact Us | 1 | 4 |  | 0 | 0
Tech Debt | Mobile after Submit Volunteer | 1 | 4 |  | 0 | 0
Tech Debt | Admin Mobile Margin and Padding | 1 | 4 |  | 0 | 0
Tech Debt | Manage Users Unusable in Mobile | 1 | 4 |  | 0 | 0
Total |  | 370 | 1940 |  | 276 | 1468
Total Weeks | 114.9346
Projected Remaining Weeks of Work | 19.9346
Elapsed Weeks | 95
Project Delay in Weeks | 33
Project Week Number Accounting for Delay | 62
Project Start Date | 2022-11-27
Estimated Completion Date | 2025-02-09 13:01
Average Points Completed Per Week | 4.4516
Average Hours Completed Per Week | 23.6774
Remaining Hours | 472
Project Percent Complete | 75.67%

## Burn Down
Date | Week Number | Remaining Hours
2024-08-12 | 56 | 568
2024-08-19 | 57 | 704
2024-08-26 | 58 | 732
2024-09-02 | 59 | 728
2024-09-09 | 60 | 664
2024-09-23 | 62 | 472

## Points
Points | Complexity | Hours
1 | Dead Simple | 4
2 | Low | 8
3 | Medium | 16
5 | High | 32
8 | Too Complex, Break Up | 64

## Resources
Name | Dedicated Development Hours Per Week
Greg Finzer | 8
James MacIvor | 0
Val Skordin | 10
Total | 18

## Variables
Variable | Value
Start Date | 2022-11-27