## Estimates
Epic | Story | Points | Estimated Hours | Completed | Completed Points | Completed Hours
Project Setup | Information Architecture Diagram | 1 | 4 | TRUE | 1 | 4
Project Setup | Define Roles | 1 | 4 | TRUE | 1 | 4
Project Setup | Git Repository | 1 | 4 | TRUE | 1 | 4
Project Setup | Visual Studio Solution | 1 | 4 | TRUE | 1 | 4
Project Setup | AppVeyor Build Pipeline | 1 | 4 | TRUE | 1 | 4
Project Setup | Static Code Quality Analysis | 1 | 4 | TRUE | 1 | 4
Project Setup | Project Plan | 2 | 8 | TRUE | 2 | 8
Project Setup | Implementation Plan | 2 | 8 | TRUE | 2 | 8
Project Setup | Application Infrastructure Diagram | 1 | 4 | TRUE | 1 | 4
Project Setup | Application Architecture Diagram | 1 | 4 | TRUE | 1 | 4
Project Setup | Entity Relationship Diagram | 2 | 8 | TRUE | 2 | 8
Project Setup | Admin Blazor Module | 1 | 4 | TRUE | 1 | 4
Project Setup | Entity Framework | 2 | 8 | TRUE | 2 | 8
Project Setup | Estimates | 1 | 4 | TRUE | 1 | 4
Project Setup | Entity Framework Models | 2 | 8 | TRUE | 2 | 8
Project Setup | Serilog Console, File Logging | 2 | 8 | TRUE | 2 | 8
Project Setup | Code Quality Check Razor Pages | 1 | 4 | TRUE | 1 | 4
Project Setup | Code Quality Check Async Methods | 1 | 4 | TRUE | 1 | 4
Project Setup | Setup Deployment | 3 | 16 | TRUE | 3 | 16
Home Page | Home Page Header | 3 | 16 | TRUE | 3 | 16
Home Page | Image Rotator | 2 | 8 | TRUE | 2 | 8
Home Page | Home Page Middle | 2 | 8 | TRUE | 2 | 8
Home Page | Home Page Footer | 2 | 8 | TRUE | 2 | 8
Basic Administration | Login | 3 | 16 | TRUE | 3 | 16
Basic Administration | Logout | 2 | 8 | TRUE | 2 | 8
Basic Administration | Administration Dashboard | 3 | 16 | TRUE | 3 | 16
Basic Administration | Edit Configuration | 5 | 32 | TRUE | 5 | 32
Basic Administration | Edit Home Page | 5 | 32 |  | 0 | 0
Basic Administration | Edit Header | 5 | 32 | TRUE | 5 | 32
Basic Administration | Edit Footer | 5 | 32 | TRUE | 5 | 32
Manage Images and Videos | List Images and Videos | 5 | 32 | TRUE | 5 | 32
Manage Images and Videos | Upload Image | 3 | 16 | TRUE | 3 | 16
Manage Images and Videos | View Image | 2 | 8 | TRUE | 2 | 8
Manage Images and Videos | Delete Image | 2 | 8 | TRUE | 2 | 8
Manage Images and Videos | Rename Image | 2 | 8 | TRUE | 2 | 8
Manage Images and Videos | New Folder | 1 | 4 | TRUE | 1 | 4
Manage Web Pages | List Pages | 3 | 16 | TRUE | 3 | 16
Manage Web Pages | Add Page | 5 | 32 |  | 0 | 0
Manage Web Pages | Edit Page | 2 | 8 |  | 0 | 0
Manage Web Pages | Delete Page | 2 | 8 |  | 0 | 0
Manage Web Pages | Rename Page | 2 | 8 |  | 0 | 0
National Pages | National About Us Page | 2 | 8 | TRUE | 2 | 8
National Pages | National History of Bed Brigade Page | 2 | 8 | TRUE | 2 | 8
Locations | Location List | 3 | 16 | TRUE | 3 | 16
Locations | Grove City Location Home Page | 3 | 16 |  | 0 | 0
Locations | Polaris Location Home Page | 3 | 16 |  | 0 | 0
Locations | Bed Brigade Near Me | 5 | 32 | TRUE | 5 | 32
Locations | Grove City Assembly Instructions | 2 | 8 |  | 0 | 0
Locations | Polaris Assembly Instructions | 2 | 8 |  | 0 | 0
Locations | Grove City Partners | 2 | 8 |  | 0 | 0
Manage Locations | Manage Locations Page | 5 | 32 | TRUE | 5 | 32
Manage Locations | Edit Location | 3 | 16 | TRUE | 3 | 16
Manage Locations | Add Location | 5 | 32 | TRUE | 5 | 32
Manage Locations | Deactivate/Activate Location | 2 | 8 |  | 0 | 0
Location Request Bed | Request Bed Page | 5 | 32 |  | 0 | 0
Location Request Bed | Manage Bed Requests | 5 | 32 | TRUE | 5 | 32
Location Request Bed | Schedule Deliveries | 5 | 32 |  | 0 | 0
Location Request Bed | Delivery Checklist | 3 | 16 |  | 0 | 0
Location Request Bed | Bulk Email Scheduled Deliveries | 5 | 32 |  | 0 | 0
Location Volunteer | Volunteer Page | 5 | 32 |  | 0 | 0
Location Volunteer | Manage Volunteers | 5 | 32 | TRUE | 5 | 32
Location Volunteer | Bulk Email Volunteers | 3 | 16 |  | 0 | 0
Location Volunteer | Manage Build and Delivery Schedule | 5 | 32 |  | 0 | 0
Location Contact Us | Contact Us Page | 3 | 16 |  | 0 | 0
Location Contact Us | Manage Contacts | 5 | 32 |  | 0 | 0
Location Donations | Setup Paypal IPN | 5 | 32 |  | 0 | 0
Location Donations | Grove City Donate | 3 | 16 |  | 0 | 0
Location Donations | Polaris Donate | 3 | 16 |  | 0 | 0
Location Donations | Manage Donations | 5 | 32 |  | 0 | 0
Location Donations | Email Tax Forms | 5 | 32 |  | 0 | 0
Manage Users | User List | 3 | 16 | TRUE | 3 | 16
Manage Users | Add User | 3 | 16 | TRUE | 3 | 16
Manage Users | Edit User | 3 | 16 | TRUE | 3 | 16
Manage Users | Delete User | 3 | 16 | TRUE | 3 | 16
News | National News Sample Story | 3 | 16 |  | 0 | 0
News | List of News | 3 | 16 |  | 0 | 0
News | News Detail | 3 | 16 |  | 0 | 0
News | Manage News | 3 | 16 |  | 0 | 0
News | Add News | 3 | 16 |  | 0 | 0
News | Edit News | 3 | 16 |  | 0 | 0
News | Delete News | 2 | 8 |  | 0 | 0
Stories | Grove City Sample Story | 2 | 8 |  | 0 | 0
Stories | Polaris Sample Story | 2 | 8 |  | 0 | 0
Stories | List of Stories | 2 | 8 |  | 0 | 0
Stories | Story Detail | 2 | 8 |  | 0 | 0
Stories | Manage Stories | 2 | 8 |  | 0 | 0
Stories | Add Story | 2 | 8 |  | 0 | 0
Stories | Edit Story | 2 | 8 |  | 0 | 0
Stories | Delete Story | 2 | 8 |  | 0 | 0
Total |  | 250 | 1340 |  | 124 | 652
Total Weeks | 28.5106
Projected Remaining Weeks of Work | 31.6564
Week Number | 30
Project Start Date | 2022-11-27
Estimated Completion Date | 2024-02-07 14:17
Average Points Completed Per Week | 4.1333
Average Hours Completed Per Week | 21.7333

## Deprioritized
Epic | Story | Points | Estimated Hours | Completed | Completed Points | Completed Hours
Search | Search Indexing | 5 | 32 |  | 1 | 4
Search | Search Bar | 3 | 16 |  | 1 | 4
Search | Search Results | 5 | 32 |  | 1 | 4
Advanced Features | Remove Image Geolocation | 2 | 8 |  | 1 | 4
Advanced Features | Convert Image to WebP | 2 | 8 |  | 1 | 4
Advanced Features | Page Versioning | 5 | 32 |  | 1 | 4
Advanced Features | Page History | 5 | 32 |  | 2 | 8
Advanced Features | Restore Version | 5 | 32 |  | 2 | 8
Total De-prioritized |  | 32 | 192

## Points
Points | Complexity | Hours
1 | Dead Simple | 4
2 | Low | 8
3 | Medium | 16
5 | High | 32
8 | Too Complex, Break Up | 64

## Resources
Name | Dedicated Development Hours Per Week
Greg Finzer | 8
James MacIvor | 4
Mike Chafin | 25
Val Skordin | 10
Total | 47

## Variables
Variable | Value
Start Date | 2022-11-27