## Estimates
Epic | Story | Points | Estimated Hours | Completed | Completed Points | Completed Hours
Project Setup | Information Architecture Diagram | 1 | 4 | TRUE | 1 | 4
Project Setup | Define Roles | 1 | 4 | TRUE | 1 | 4
Project Setup | Git Repository | 1 | 4 | TRUE | 1 | 4
Project Setup | Visual Studio Solution | 1 | 4 | TRUE | 1 | 4
Project Setup | AppVeyor Build Pipeline | 1 | 4 | TRUE | 1 | 4
Project Setup | Static Code Quality Analysis | 1 | 4 | TRUE | 1 | 4
Project Setup | Project Plan | 2 | 8 | TRUE | 2 | 8
Project Setup | Implementation Plan | 2 | 8 | TRUE | 2 | 8
Project Setup | Application Infrastructure Diagram | 1 | 4 | TRUE | 1 | 4
Project Setup | Application Architecture Diagram | 1 | 4 | TRUE | 1 | 4
Project Setup | Entity Relationship Diagram | 2 | 8 | TRUE | 2 | 8
Project Setup | Admin Blazor Module | 1 | 4 | TRUE | 1 | 4
Project Setup | Entity Framework | 2 | 8 | TRUE | 2 | 8
Project Setup | Estimates | 1 | 4 | TRUE | 1 | 4
Project Setup | Entity Framework Models | 2 | 8 | TRUE | 2 | 8
Project Setup | Serilog Console, File Logging | 2 | 8 | TRUE | 2 | 8
Project Setup | Code Quality Check Razor Pages | 1 | 4 | TRUE | 1 | 4
Project Setup | Code Quality Check Async Methods | 1 | 4 | TRUE | 1 | 4
Project Setup | Setup Deployment | 3 | 16 | TRUE | 3 | 16
Home Page | Home Page Header | 3 | 16 | TRUE | 3 | 16
Home Page | Image Rotator | 2 | 8 | TRUE | 2 | 8
Home Page | Home Page Middle | 2 | 8 | TRUE | 2 | 8
Home Page | Home Page Footer | 2 | 8 | TRUE | 2 | 8
Basic Administration | Login | 3 | 16 | TRUE | 3 | 16
Basic Administration | Logout | 2 | 8 | TRUE | 2 | 8
Basic Administration | Administration Dashboard | 3 | 16 | TRUE | 3 | 16
Basic Administration | Edit Configuration | 5 | 32 | TRUE | 5 | 32
Basic Administration | Edit Home Page | 5 | 32 | TRUE | 5 | 32
Basic Administration | Edit Header | 5 | 32 | TRUE | 5 | 32
Basic Administration | Edit Footer | 5 | 32 | TRUE | 5 | 32
Manage Images and Videos | List Images and Videos | 5 | 32 | TRUE | 5 | 32
Manage Images and Videos | Upload Image | 3 | 16 | TRUE | 3 | 16
Manage Images and Videos | View Image | 2 | 8 | TRUE | 2 | 8
Manage Images and Videos | Delete Image | 2 | 8 | TRUE | 2 | 8
Manage Images and Videos | Rename Image | 2 | 8 | TRUE | 2 | 8
Manage Images and Videos | New Folder | 1 | 4 | TRUE | 1 | 4
Manage Web Pages | List Pages | 3 | 16 | TRUE | 3 | 16
Manage Web Pages | Add Page | 5 | 32 | TRUE | 5 | 32
Manage Web Pages | Edit Page | 2 | 8 | TRUE | 2 | 8
Manage Web Pages | Delete Page | 2 | 8 | TRUE | 2 | 8
Manage Web Pages | Rename Page | 2 | 8 | TRUE | 2 | 8
National Pages | Design National Home Page | 5 | 32 | TRUE | 5 | 32
National Pages | National Home Page | 5 | 32 | TRUE | 5 | 32
National Pages | National About Us Page | 2 | 8 | TRUE | 2 | 8
National Pages | National History of Bed Brigade Page | 2 | 8 |  | 0 | 0
Locations | Location List | 3 | 16 | TRUE | 3 | 16
Locations | Bed Brigade Near Me | 5 | 32 | TRUE | 5 | 32
Locations | Grove City Location Home Page | 3 | 16 | TRUE | 3 | 16
Locations | Grove City Location About Us Page | 2 | 8 | TRUE | 2 | 8
Locations | Grove City History Page | 2 | 8 | TRUE | 2 | 8
Locations | Grove City Partners | 2 | 8 | TRUE | 2 | 8
Locations | Grove City Assembly Instructions | 2 | 8 | TRUE | 2 | 8
Locations | Polaris Location Home Page | 5 | 32 | TRUE | 5 | 32
Locations | Polaris About Us Page | 2 | 8 | TRUE | 2 | 8
Locations | Polaris History | 2 | 8 | TRUE | 2 | 8
Manage Locations | Manage Locations Page | 5 | 32 | TRUE | 5 | 32
Manage Locations | Edit Location | 3 | 16 | TRUE | 3 | 16
Manage Locations | Add Location | 5 | 32 | TRUE | 5 | 32
Manage Locations | Deactivate/Activate Location | 5 | 32 | TRUE | 5 | 32
Location Request Bed | Request Bed Page | 5 | 32 | TRUE | 5 | 32
Location Request Bed | Manage Bed Requests | 5 | 32 | TRUE | 5 | 32
Location Request Bed | Manage Delivery Checklist | 5 | 32 | TRUE | 5 | 32
Location Volunteer | Volunteer Page | 5 | 32 | TRUE | 5 | 32
Location Volunteer | Manage Volunteers | 5 | 32 | TRUE | 5 | 32
Location Volunteer | Bulk Email Volunteers | 3 | 16 | TRUE | 3 | 16
Location Volunteer | Manage Build and Delivery Schedule | 5 | 32 | TRUE | 5 | 32
Location Contact Us | Contact Us Page | 3 | 16 | TRUE | 3 | 16
Location Contact Us | Manage Contacts | 5 | 32 | TRUE | 5 | 32
Location Donations | Grove City Donate | 3 | 16 | TRUE | 3 | 16
Location Donations | Polaris Donate | 3 | 16 |  | 0 | 0
Location Donations | Manage Donations | 5 | 32 | TRUE | 5 | 32
Location Donations | Email Tax Forms | 5 | 32 | TRUE | 5 | 32
Manage Users | User List | 3 | 16 | TRUE | 3 | 16
Manage Users | Add User | 3 | 16 | TRUE | 3 | 16
Manage Users | Edit User | 3 | 16 | TRUE | 3 | 16
Manage Users | Delete User | 3 | 16 | TRUE | 3 | 16
Stories | Grove City Sample Story | 2 | 8 | TRUE | 2 | 8
Stories | Polaris Sample Story | 2 | 8 | TRUE | 2 | 8
Stories | List of Stories | 3 | 16 | TRUE | 3 | 16
Stories | Story Detail | 3 | 16 | TRUE | 3 | 16
Stories | Manage Stories | 3 | 16 | TRUE | 3 | 16
Stories | Add Story | 3 | 16 | TRUE | 3 | 16
Stories | Edit Story | 1 | 4 | TRUE | 1 | 4
Stories | Delete Story | 1 | 4 | TRUE | 1 | 4
News | National News Sample Story | 3 | 16 | TRUE | 3 | 16
News | List of News | 3 | 16 | TRUE | 3 | 16
News | News Detail | 3 | 16 | TRUE | 3 | 16
News | Manage News | 3 | 16 | TRUE | 3 | 16
News | Add News | 3 | 16 | TRUE | 3 | 16
News | Edit News | 1 | 4 | TRUE | 1 | 4
News | Delete News | 1 | 4 | TRUE | 1 | 4
Tech Debt | Upgrade to Blazor 8 | 5 | 32 | TRUE | 5 | 32
Tech Debt | Refactor Common.cs | 1 | 4 | TRUE | 1 | 4
Tech Debt | Refactor into Files | 1 | 4 | TRUE | 1 | 4
Tech Debt | Move Entities | 1 | 4 | TRUE | 1 | 4
Tech Debt | Move Syncfusion Licensing | 1 | 4 | TRUE | 1 | 4
Tech Debt | Regression Testing | 3 | 16 | TRUE | 3 | 16
Tech Debt | Change from Azure Email to SmarterASP.NET Email | 1 | 4 | TRUE | 1 | 4
Tech Debt | Update Diagrams | 1 | 4 | TRUE | 1 | 4
Tech Debt | GitHub Actions for Pull Requests | 1 | 4 | TRUE | 1 | 4
Tech Debt | Deploy to SmarterASP.NET Development | 1 | 4 | TRUE | 1 | 4
Tech Debt | Use location query parm Bed Request | 1 | 4 | TRUE | 1 | 4
Tech Debt | Use Location Query Parm Contact | 1 | 4 | TRUE | 1 | 4
Tech Debt | Use Location Query Parm Volunteer | 1 | 4 | TRUE | 1 | 4
Tech Debt | Design Shared Bed Requests | 1 | 4 | TRUE | 1 | 4
Tech Debt | Admin Dashboard Content | 1 | 4 | TRUE | 1 | 4
Tech Debt | Unique Volunteer Email Add Dialog | 1 | 4 | TRUE | 1 | 4
Tech Debt | Update NuGet Packages and Change NUnit Assertions | 2 | 8 | TRUE | 2 | 8
Tech Debt | Cache get files | 1 | 4 | TRUE | 1 | 4
Tech Debt | Remove Unused Components and Pages | 1 | 4 |  | 0 | 0
Tech Debt | Add three image rotators to Bed Brigade Near Me | 1 | 4 | TRUE | 1 | 4
Tech Debt | Protected Directories | 5 | 32 | TRUE | 5 | 32
Tech Debt | Verify security for all pages | 3 | 16 |  | 0 | 0
Tech Debt | Global Error Handler | 3 | 16 | TRUE | 3 | 16
Tech Debt | Refresh Header and Footer | 1 | 4 | TRUE | 1 | 4
Tech Debt | Add Page Titles | 1 | 4 | TRUE | 1 | 4
Tech Debt | AppOffline for Development | 2 | 8 | TRUE | 2 | 8
Tech Debt | Syncfusion Spinner | 2 | 8 | TRUE | 2 | 8
Tech Debt | Re-add compilerconfig.json | 1 | 4 | TRUE | 1 | 4
Tech Debt | Rework Seeding | 2 | 8 | TRUE | 2 | 8
Tech Debt | Add Notification Code to Sorry Page | 1 | 4 | TRUE | 1 | 4
Manage Locations | Metro Areas | 1 | 4 | TRUE | 1 | 4
Locations | Polaris Donations Page | 3 | 16 |  | 0 | 0
New Stories | Send confirmation email for Bed Request | 1 | 4 | TRUE | 1 | 4
Tech Debt | Make seeding environment specific | 1 | 4 | TRUE | 1 | 4
Tech Debt | Import Bed Requests | 3 | 16 |  | 0 | 0
Tech Debt | Add Database Indexes | 1 | 4 | TRUE | 1 | 4
Tech Debt | Verify Mobile for all pages | 1 | 4 | TRUE | 1 | 4
Tech Debt | Refactor Grid Persistence | 2 | 8 | TRUE | 2 | 8
Tech Debt | Add try catch and alert | 3 | 16 |  | 0 | 0
National Pages | National History of Bed Brigade Page | 1 | 4 |  | 0 | 0
National Pages | National Donations Page | 1 | 4 | TRUE | 1 | 4
Location Request Bed | Download Delivery Sheet | 5 | 32 | TRUE | 5 | 32
Location Volunteer | Manage Sign Ups | 5 | 32 | TRUE | 5 | 32
Tech Debt | Seed Only Grove City and Rock City | 1 | 4 | TRUE | 1 | 4
Tech Debt | Bed Request Added to List and Team # | 1 | 4 | TRUE | 1 | 4
Tech Debt | Location Timezone | 3 | 16 | TRUE | 3 | 16
Tech Debt | Redo Manage Bed Request Form | 1 | 4 | TRUE | 1 | 4
Tech Debt | Delivery Sheet Sort By Team Then By Distance | 1 | 4 | TRUE | 1 | 4
Tech Debt | Add Delivery Checklist to the Delivery Sheet | 1 | 4 | TRUE | 1 | 4
Tech Debt | Use Animate.css and Wow.js | 1 | 4 | TRUE | 1 | 4
Tech Debt | Migration Deployment Setup Database and Preload | 1 | 4 | TRUE | 1 | 4
Tech Debt | Improve Performance | 3 | 16 | TRUE | 3 | 16
Tech Debt | Edit EmailTaxForm | 1 | 4 | TRUE | 1 | 4
Tech Debt | Create Custom Authentication | 1 | 4 | TRUE | 1 | 4
Tech Debt | Create Server Information Page | 1 | 4 | TRUE | 1 | 4
Tech Debt | Refresh Header and Footer | 1 | 4 | TRUE | 1 | 4
Tech Debt | Refactor Grid Persistence | 2 | 8 | TRUE | 2 | 8
Tech Debt | Seed Only Grove City and Rock City | 1 | 4 | TRUE | 1 | 4
Tech Debt | Download Delivery Sheet | 5 | 32 | TRUE | 5 | 32
Tech Debt | Mobile Bed Brigade Near Me | 1 | 4 | TRUE | 1 | 4
Tech Debt | Mobile After Submit Bed Request | 1 | 4 | TRUE | 1 | 4
Tech Debt | Mobile after Contact Us | 1 | 4 | TRUE | 1 | 4
Tech Debt | Mobile after Submit Volunteer | 1 | 4 | TRUE | 1 | 4
Tech Debt | Admin Mobile Margin and Padding | 1 | 4 | TRUE | 1 | 4
Tech Debt | Manage Users Unusable in Mobile | 1 | 4 | TRUE | 1 | 4
Tech Debt | Design Spanish Translation | 2 | 8 | TRUE | 2 | 8
Tech Debt | Address Autocomplete Design | 1 | 4 | TRUE | 1 | 4
Tech Debt | Design Bulk Email Mailing List | 1 | 4 | TRUE | 1 | 4
Tech Debt | Donations Design | 1 | 4 | TRUE | 1 | 4
Tech Debt | SMS Design | 2 | 8 | TRUE | 2 | 8
New Stories | Calendar | 2 | 8 | TRUE | 2 | 8
New Stories | Upcoming Events | 5 | 32 | TRUE | 5 | 32
New Stories | Add new Schedule Fields | 2 | 8 | TRUE | 2 | 8
New Stories | New Manage Volunteer Fields | 2 | 8 | TRUE | 2 | 8
New Stories | Volunteer Sign Up New Fields | 2 | 8 | TRUE | 2 | 8
New Stories | New Manage Bed Request Fields | 2 | 8 | TRUE | 2 | 8
New Stories | New Bed Request Form Fields | 2 | 8 | TRUE | 2 | 8
Tech Debt | Bust Browser Cache for New Version | 1 | 4 | TRUE | 1 | 4
New Stories | Localizable String Parsing | 3 | 16 | TRUE | 3 | 16
New Stories | Localize Strings | 2 | 8 | TRUE | 2 | 8
New Stories | Test Non-Localized Strings | 1 | 4 | TRUE | 1 | 4
New Stories | Localize Validation Messages | 3 | 16 | TRUE | 3 | 16
New Stories | Localize Drop Downs | 3 | 16 | TRUE | 3 | 16
New Stories | Save Messages Localization | 2 | 8 | TRUE | 2 | 8
Tech Debt | Delivery Sheet Slow | 2 | 8 | TRUE | 2 | 8
Tech Debt | Update Documentation for Localization | 1 | 4 | TRUE | 1 | 4
New Stories | Send Confirmation Email for Volunteer Sign Up | 2 | 8 | TRUE | 2 | 8
New Stories | Localize Dynamic Content | 3 | 16 | TRUE | 3 | 16
Tech Debt | Make EmailQueue into a Background Service | 1 | 4 | TRUE | 1 | 4
Tech Debt | Menu not wide enough when translated to Spanish | 1 | 4 | TRUE | 1 | 4
New Stories | Apply String Localization | 3 | 16 | TRUE | 3 | 16
Tech Debt | Going to Events loads National Header and Footer | 1 | 4 | TRUE | 1 | 4
Tech Debt | Data Attribute Validation | 1 | 4 | TRUE | 1 | 4
Address | Location Latitude & Longitude | 1 | 4 | TRUE | 1 | 4
Address | Geolocation of Address | 3 | 16 | TRUE | 3 | 16
Address | Geolocation Routing | 2 | 8 |  | 0 | 0
Donations | New Donation Fields | 1 | 4 |  | 0 | 0
Donations | Donation Campaign Table | 1 | 4 |  | 0 | 0
Donations | Seed Donation Campaign | 1 | 4 |  | 0 | 0
Donations | Stripe Seed Configuration | 1 | 4 |  | 0 | 0
Donations | Stripe Processing Code | 5 | 32 |  | 0 | 0
Donations | Paypal IPN Handler | 5 | 32 |  | 0 | 0
Donations | Donations Sum By Campaign Name | 2 | 8 |  | 0 | 0
Donations | Edit Donations Page | 3 | 16 |  | 0 | 0
Newsletter | Create Newsletter Tables | 1 | 4 | TRUE | 1 | 4
Newsletter | Manage Newsletters | 2 | 8 | TRUE | 2 | 8
Newsletter | Subscribe/Unsubscribe to Newsletter Page | 3 | 16 | TRUE | 3 | 16
Newsletter | Ability to Send Newsletters | 3 | 16 | TRUE | 3 | 16
SMS | Add LocationId to Configuration with a default of National | 1 | 4 | TRUE | 1 | 4
SMS | Create Code for SMS Queue | 2 | 8 | TRUE | 2 | 8
Tech Debt | Admin Clear Cache | 1 | 4 | TRUE | 1 | 4
Tech Debt | Manage Configuration Location | 1 | 4 | TRUE | 1 | 4
Custom Media Manager | Custom Media Manager | 5 | 32 | TRUE | 5 | 32
Custom Media Manager | Media Manager Cut, Copy, Paste Files | 1 | 4 | TRUE | 1 | 4
Custom Media Manager | Media Manager Refactoring | 1 | 4 | TRUE | 1 | 4
SMS | Add LocationId to Configuration with a default of National | 1 | 4 | TRUE | 1 | 4
SMS | Design send and receive SMS Messages and Reply | 2 | 8 | TRUE | 2 | 8
SMS | SMS Table | 1 | 4 | TRUE | 1 | 4
SMS | SMS Database Indexes | 1 | 4 | TRUE | 1 | 4
SMS | SMS Message Summary | 3 | 16 | TRUE | 3 | 16
SMS | SMS Message Detail | 3 | 16 | TRUE | 3 | 16
SMS | SMS Controller and Test Harness | 3 | 16 | TRUE | 3 | 16
SMS | Bulk SMS | 3 | 16 | TRUE | 3 | 16
SMS | SMS Missed Messages | 2 | 8 | TRUE | 2 | 8
SMS | Re-Style Summary Page | 3 | 16 | TRUE | 3 | 16
SMS | SMS Delete Old Records | 1 | 4 | TRUE | 1 | 4
Tech Debt | Fix Publish | 3 | 16 | TRUE | 3 | 16
Tech Debt | Shutdown Background Services | 2 | 8 | TRUE | 2 | 8
New Stories | Laptop Admin Dialogs | 1 | 4 | TRUE | 1 | 4
New Stories | Generated Next Events | 5 | 32 | TRUE | 5 | 32
New Stories | Generated Carousel | 5 | 32 | TRUE | 5 | 32
Total |  | 503 | 2604 |  | 463 | 2396
Total Weeks | 134.0735
Projected Remaining Weeks of Work | 8.0735
Elapsed Weeks | 126
Project Delay in Weeks | 33
Project Week Number Accounting for Delay | 93
Project Start Date | 2022-11-27
Estimated Completion Date | 2025-06-23 12:20
Average Points Completed Per Week | 4.9785
Average Hours Completed Per Week | 25.7634
Remaining Hours | 208
Project Percent Complete | 92.01%

## Burn Down
Date | Week Number | Remaining Hours | Difference | Note
2024-08-12 | 56 | 568 | 0
2024-08-19 | 57 | 704 | 136
2024-08-26 | 58 | 732 | 28
2024-09-02 | 59 | 728 | -4
2024-09-09 | 60 | 664 | -64
2024-09-23 | 62 | 472 | -192
2024-09-30 | 63 | 472 | 0
2024-10-07 | 64 | 548 | 76
2024-10-14 | 65 | 524 | -24
2024-10-21 | 66 | 492 | -32
2024-10-28 | 67 | 444 | -48
2024-11-04 | 68 | 632 | 188 | New Donations, SMS, Address, Newsletter
2024-11-11 | 69 | 612 | -20
2024-11-18 | 70 | 588 | -24
2024-11-25 | 71 | 588 | 0 | Vacation and Leyla Medical Problems
2024-12-02 | 72 | 588 | 0 | Vacation and Leyla Medical Problems
2024-12-09 | 73 | 588 | 0 | Vacation and Leyla Medical Problems
2024-12-16 | 74 | 588 | 0 | Vacation and Leyla Medical Problems
2024-12-23 | 75 | 588 | 0 | Vacation and Leyla Medical Problems
2024-12-30 | 76 | 588 | 0 | Vacation and Leyla Medical Problems
2025-01-06 | 77 | 588 | 0 | Vacation and Leyla Medical Problems
2025-01-13 | 78 | 588 | 0 | Vacation and Leyla Medical Problems
2025-01-20 | 79 | 588 | 0 | Vacation and Leyla Medical Problems
2025-01-27 | 80 | 528 | -60
2025-02-03 | 81 | 518 | -10
2025-02-10 | 82 | 508 | -10
2025-02-17 | 83 | 498 | -10
2025-02-24 | 84 | 488 | -10
2025-03-03 | 85 | 480 | -8
2025-03-10 | 86 | 480 | 0
2025-03-17 | 87 | 480 | 0
2025-03-24 | 88 | 480 | 0
2025-03-31 | 89 | 480 | 0
2025-04-07 | 90 | 480 | 0
2025-04-14 | 91 | 480 | 0
2025-04-21 | 92 | 480 | 0
2025-04-28 | 93 | 208 | -272 | Val turned in News and Stories feature all at once.
Formulas:
Date = [Date, row above]+7

## Points
Points | Complexity | Hours
1 | Dead Simple | 4
2 | Low | 8
3 | Medium | 16
5 | High | 32
8 | Too Complex, Break Up | 64

## Resources
Name | Dedicated Development Hours Per Week
Greg Finzer | 8
James MacIvor | 0
Val Skordin | 10
Total | 18

## Variables
Variable | Value
Start Date | 2022-11-27